NESTOR Phase 2

Action Plan & Open Items

May 2026 / For discussion

# 1. Experimental Conditions

All conditions apply to both FOL and Coq pipelines. Think about what each condition tests and how prompts change.

| Condition | Setup | What it tests |
| --- | --- | --- |
| C1 | Blind: no label given to LLM | Can the LLM decide entailment/contradiction/neutral AND formalise it? |
| C2 | Phase 1 predictions as labels | Does giving the LLM its own previous NLI judgment help formalisation? |
| C3 | Gold label given directly | Given the correct answer, can the LLM produce valid formal proof? |
| C4 | Gold label + NL explanation | Does a chain-of-thought explanation improve formalisation quality? |

Key questions for you to consider:

- C1 is the hardest: the LLM must do NLI + formalisation simultaneously. Start here or with C3?

- C2 uses fracas_results_azure.json from Phase 1. How do we load and inject these predictions?

- C4 (Valentino): where does the explanation come from? A separate LLM call? A fixed template?

# 2. FOL Track

## 2.1 Current state

- fol_pipeline.py works end-to-end: NL to FOL to Prover9/MACE4 to result

- C1 blind mode runs. C2/C3/C4 need prompt modifications.

- nl_to_fol.txt is bare: just says "translate to FOL, use Prover9 syntax"

## 2.2 Prompt tiers (to discuss)

Should we enrich the FOL prompt? If so, how much?

| Tier | What the prompt contains | Discussion point |
| --- | --- | --- |
| F0 | Current: bare syntax instructions only | Baseline. LLM uses its own FOL knowledge. |
| F1 | + naming conventions, arity rules, variable binding constraints | Reduces syntax errors without imposing theory. Worth doing? |
| F2 | + theory specification: plain predicate logic vs Davidsonian events | Do we want all models using the same theory? Or let them choose? |

Open questions:

- Davidsonian events add expressiveness (thematic roles, modifiers) but complexity. Is it worth it for FraCaS?

- Should we enforce consistent predicate naming across items? e.g., always man(x) not Man(x)?

- F0 vs F1 vs F2 is itself an ablation study: do we have time/budget for all three?

# 3. Coq Track

## 3.1 Current state

- coq_pipeline.py exists: supports direct + valentino approaches, verification loop (k=3)

- Never been run: results folder is empty

- nl_to_coq.txt is essentially empty: just Parameter Entity : Type with no theory

- 44 Coq foundation files now in coq_foundations/ (Montague, MTT, GQ, plurals, tense, etc.)

## 3.2 Prompt tiers (to discuss)

The Coq prompt can include foundation files as context. How much context helps?

| Tier | What the prompt contains | Discussion point |
| --- | --- | --- |
| T0 | Coq syntax instructions only, no theory files | Analogous to F0. Tests LLM's built-in Coq knowledge. |
| T1 | + Montague.v (~140 lines, ~500 tokens) | Minimal theory. Does a single file help? |
| T2 | + 2-4 section-matched files (2-8K tokens) | Targeted theory per FraCaS section. Best effort-to-gain ratio? |
| T3 | + 5-8 files, full theory stack (10-20K tokens) | Rich context. Only feasible on GPT-4o / Llama-70B. |

## 3.3 Section to foundation file mapping (draft)

For T2/T3, which files go with which FraCaS section?

| FraCaS Section | T2 files (2-4) | T3 adds |
| --- | --- | --- |
| 1. Quantifiers | Montague.v, BarwiseCooper.v | Quantifiers.v, DonkeyScope.v |
| 2. Plurals | Link1983.v, Montague.v | champollion_full.v |
| 3. Anaphora | DonkeyScope.v, Montague.v | BarwiseCooper.v |
| 4. Ellipsis | Montague.v | - |
| 5. Adjectives | AdjectivesExtension.v, MTT_base.v | Quantifiers.v |
| 6. Comparatives | AdjectivesExtension.v, Montague.v | MTT_base.v |
| 7. Temporal | DowtyTense.v, Montague.v | Aspect.v, ImperfectiveParadox.v |
| 8. Verbs/Attitudes | PTQ.v, kratzer2.v | PTQ_deep.v |
| 9. Nominalization | MTT_base.v, Montague.v | - |

This mapping is a starting point. Review and adjust based on what the items actually require.

# 4. Model Context Limits

Not all models can handle rich prompts. Plan accordingly:

| Model | Context window | Safe Coq budget | Max tier |
| --- | --- | --- | --- |
| GPT-4o | 128K | ~100K tokens | T3 (full stack) |
| DeepSeek-R1 | 64K | ~50K | T2-T3 (careful) |
| Llama-3.3-70B | 128K | ~100K | T3 |
| Llama-8B / Krikri-8B | 128K nominal | ~10-15K effective | T0-T1 only |

Small models degrade with long context even if they technically accept it. Keep T2/T3 for big models only.

# 5. Action Items

| # | Task | Who | Priority |
| --- | --- | --- | --- |
| 1 | Write Coq T0 prompt (syntax-only, no theory) | Stergios + team | High, do first |
| 2 | Write FOL F1 prompt (add consistency rules) | Stergios + team | High |
| 3 | First test run: Coq T0 + C3 on 10 FraCaS items | Students | High, validates pipeline |
| 4 | First test run: FOL F0 + C1 on 10 items (already works?) | Students | High, confirms baseline |
| 5 | Build C2 data loader (read Phase 1 predictions, inject as labels) | Students | Medium |
| 6 | Build prompt builder function (section to foundation files) | Students | Medium |
| 7 | Decide: Montague vs MTT vs both for Coq experiments | Team discussion | Medium, affects T1+ |
| 8 | Decide: Davidsonian vs plain for FOL experiments | Team discussion | Medium |
| 9 | Add Greek FraCaS data loader | Students | Low, after English works |
| 10 | Bump max_tokens in coq_pipeline.py (1000 to 2500+) | Students | Low, quick fix |
| 11 | Define results JSON schema + scoring logic | Stergios + team | Before full runs |

# 6. Suggested Order of Work

This is a suggestion, not a mandate. Discuss and adjust.

- Write T0 + F1 prompts (we can do this together)

- Test run: 10 items, C3, one model. Does the pipeline actually work?

- Fix any pipeline bugs found in step 2

- Run C1 + C3 across all models on full FraCaS (T0/F0 prompts)

- Build T1/T2 prompts, run ablation

- Add C2 + C4 conditions

- Greek data (if time permits)

Budget reminder: we have $10K for API costs. Rich prompts (T2/T3) cost more per call. Plan runs accordingly.